## Slide 1: Project Timeline
Q1 2026 Development Roadmap

## Slide 2: Development Schedule
Task | Start Date | End Date | Duration | Status
Requirements Analysis | Jan 1 | Jan 15 | 2 weeks | Complete
System Design | Jan 16 | Feb 5 | 3 weeks | Complete
Backend Development | Feb 6 | Mar 15 | 6 weeks | In Progress
Frontend Development | Feb 20 | Mar 30 | 6 weeks | In Progress
Integration Testing | Mar 15 | Apr 5 | 3 weeks | Not Started
UAT & Bug Fixes | Apr 6 | Apr 20 | 2 weeks | Not Started
Production Deployment | Apr 21 | Apr 25 | 1 week | Not Started

## Slide 3: Key Milestones
✓ Requirements Signed Off - Jan 15
✓ Design Review Complete - Feb 5
→ Backend API Ready - Mar 15 (In Progress)
→ Frontend Integration - Mar 30 (In Progress)
○ QA Approval - Apr 5 (Pending)
○ Go-Live Date - Apr 25 (Pending)